## Disagreement Report
Contract: 70Z02323D93270001
Date/Time: 2025-01-09 15:46:59
Distribution Statement D: Distribution authorized to DHS/CG/DOD and their contractors only due to administrative or operational use. Other requests shall be referred to COMMANDANT (CG-9327).
DESTRUCTION NOTICE: Destroy this document by any method that will prevent disclosure of contents or reconstruction of the document.
DOORS SPEC ID | Excel Row | Total Agreements | Total Disagreements
WCC-SPEC-8 | 2 | 2 | 1
Specification Text:
042.1.6 ABS Rules - The ABS Rules for Building and Classing Steel Vessels Under 90 Meters (295 Feet) in Length. The 2019 version of the ABS U90M Rules shall be used in this contract. The ABS Steel Vessel Rules (SVR) 2019, is also invoked for selected technical areas to provide additional requirements.
Contractor Proposed Change Comment History:
[DEC 2023] BIRDON DOES NOT BELIEVE THAT THIS CDRL (073-002) APPLIES TO THIS REQUIREMENT. THIS IS TOO BROAD
[AUG 2023] 160-WLIC-WCC-100-050 TABLE 1 references ABS High Speed NVR 2023 as ABS SVR 2019 does not provide guidance on mesh quality
[AUG 2023] BIRDON DOES NOT BELIEVE THIS CDRL (070-001) APPLIES TO THIS SPECIFICATION. U90 GIVES NO GUIDANCE ON SPACE REQUIREMENTS
Government Adjudication Comment History:
[JUN 2024] KM: DI-073-002 Add Request CONCUR Agree - Add 073-002
[FEB 2024] GVG: Add CDRL 073-002
[SEP 2023] Concur with Birdon deletion DI 070-001
Breakdown Data:
VeriDoc Number | DI Number | CDRL Subtitle | Gov. Assessed Status
WCC-VERI-DOC-1 | 070-006 | Booklet of Ship Certifications | Awaiting Input
WCC-VERI-DOC-2 | 073-002 | Propulsion System Vibration Analysis | Pending Review
WCC-VERI-DOC-3 | 073-003 | Hull Girder, Deckhouse, Exhaust Stack, Mast, and Foundations Vibration Analysis and Report | Awaiting Input
WCC-VERI-DOC-4 | 073-007 | Resilient Mount Calculations and Sway Drawings | Disagree
WCC-VERI-DOC-5 | 074-001 | Welding and NDE Documents and Reports | Awaiting Input
WCC-VERI-DOC-6 | 085-001 | Drawing Number Assignment Report | Agree
WCC-VERI-DOC-7 | 100-003 | Structural Design Report | Pending Review
WCC-VERI-DOC-8 | 100-006 | Finite Element Analysis Report and Model | Agree
WCC-VERI-DOC-20812 | 100-003 | Structural Design Report | Pending Review
WCC-VERI-DOC-22689 | 073-002 | Propulsion System Vibration Analysis | Pending Review
Disagreement Comments:
VeriDoc: WCC-VERI-DOC-4, DI Number: 073-007
No specific government comment found for this line.
PWG assigned to resolve disagreement:
USCG POC assigned to resolve disagreement:
BIRDON POC assigned to resolve disagreement:
General Comments:
Enter general comments in the cell below: